## Feature List
Feature | Sub-Area | Planning | Design | Test Plan | Development
Users | Create New User Account | Complete | Complete | Complete | Pending
| Login to Existing User Account | Complete | Complete | Complete | Pending
| User Profile Picture | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Application Permissions | User Permissions | Complete | Complete | Complete | Pending
| User Interface | Complete | In Progress | In Progress | Pending
| Database Table | Complete | Complete | Complete | Complete
Project Permissions | User Permissions | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Navigation | Navigation User Interface | Complete | Complete | Complete | In Progress
Projects | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Theme Color | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Edit | Complete | Complete | Complete | Pending
| Search | Complete | Complete | Complete | Pending
| Download All Resources | Pending | Pending | Pending | Pending
| Download Search Results | Pending | Pending | Pending | Pending
| Database Table | Complete | Complete | Complete | Complete
Project Tags | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Search | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Project Comments | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Edit | Pending | Pending | Pending | Pending
| Search | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Project Comment Tags | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Search | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Files | Upload File | Complete | Complete | Complete | Pending
| Download File | Complete | Complete | Complete | Pending
| Data Object | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Search | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
File Tags | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
File Comments | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Edit | Pending | Pending | Pending | Pending
| Search | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
File Comment Tags | Data Object | Complete | Complete | Complete | Pending
| User Interface | Complete | Complete | Complete | Pending
| Create | Complete | Complete | Complete | Pending
| Delete | Complete | Complete | Complete | Pending
| Search | Complete | Complete | Complete | Pending
| Database Table | Complete | Complete | Complete | Complete
Tags | Database Pairing Table | Complete | Complete | Complete | Complete